## Slide 1
DEPARTMENT TRAINING
AI-Native
Software Engineering
Golden Playbook for faster, safer, evidence-based delivery
Research → Design → Plan → Implement → Validate
v1.9 Baseline Candidate

## Slide 2
只有 Vibe Coding 不夠：工作越大，AI workflow 必須更深
2
SMALL CHANGE
Talk → Change → Test
one bounded session
reversible · easy to verify
PROBLEM 1
小改字與跨 Repo Feature，
不能只用同一個 prompt / session。
P1 FEATURE
Research → Design → P0
to-tickets slices delivery
JIT plan per executing P0
PROBLEM 2
AI 寫 code 越快，寫錯、patch
與技術債也累積越快。
P2 / P3
Multiple sessions
cross-repo research
System Design · staged plans
Work 越大：Research / Design / Plan / Validate 越深。Source concept：Dex Horthy, No Vibes Allowed。

## Slide 3
這次建立的是：工程師每天能照著走的 AI Development Workflow
03
持久核心
AI models 會一直變強 · Engineering workflow / ownership / evidence 必須持久
1
Research
Problem · system · unknowns
2
Design
FR · NFR · boundary · trade-offs
3
Plan
Work Level · slices · JIT
4
Implement
Default skill · TDD · review
5
Validate
Acceptance · risk · evidence
不同大小
同一流程 · 深度不同
同一 Golden Flow 適用 P3→P0；Golden defaults 經 10+ actual pilots 淬煉，可直接使用或採 approved equivalent。

## Slide 4
先回答 Six Questions，再從 Current Stage 開始
04
SIX QUESTIONS
Location · Work Level · Archetype · Current Stage · Control Profile · Next Move
1
Research
Understand · Explore · Define
2
Design
System Design* · Feature Design
3
Plan
P1→P0 · P0→tasks JIT
4
Implement
TDD · bounded change
5
Validate
Review · fresh evidence
Release & Operate
Observe · Recover · Learn
* System Design：P3/P2 required · P1 risk-triggered · P0 normally skip

## Slide 5
P3–P0 只決定深度；以下用 P1 Feature 示範
05
P3
Product / Program
方向、architecture、Epic / Wave map
P2
Epic
跨 Feature capability、System Design、Feature map
P1
Feature
本 deck example：approved outcome → P0 slices
P0
PBI / User Story
Sprint-ready tracer bullet、independent evidence
Execution Layer · Task / Plan Step / Commit
判斷規則
1
P1 是可整體驗收 / release / control 的 Feature outcome。
2
P1 的 Plan 不是 files / tasks；先切成 P0 vertical slices。
3
P0 是 Sprint-ready、narrow but complete、可獨立驗證。
4
Task / Plan Step / Commit 位於 P0 下方，不是 Work Level。
接下來全部用 P1 Feature 示範一條具體 Golden Path。

## Slide 6
P1 Feature 的 Plan：先切 P0，再做 JIT implementation plan
06
Approved P1
Feature Design
to-tickets
P0 tracer bullets
+ Blocked by
writing-plans*
Execution Tasks
files · tests · commands
DELIVERY DECOMPOSITION
P1 → P0：每張 ticket 是 narrow but complete tracer bullet。沒有 blocker 的項目形成 execution frontier。
IMPLEMENTATION PLANNING
單一 P0 即將執行且 multi-step / risky / complex 時才產生 exact implementation plan。簡單 P0 可 inline。
禁止：先替整個 Epic / Feature 建立巨大 implementation plan。Wide refactor 使用 expand → migrate batches → contract。
藍色 = Golden default skill · writing-plans only when triggered · existing OpenSpec plan stays SSOT

## Slide 7
工程師只要記住：一張 Feature，沿 Golden Flow 走到底
7
1 · 把問題弄對
Research → Design
問：change boundary / FR / NFR？
用：codebase-research
→ brainstorming / grill-me
留：approved Feature Design
DONE WHEN
Understanding + Change Gate
2 · 把交付切小
Plan → Implement
to-tickets → P0 vertical slices
Blocked by → execution frontier
writing-plans → JIT tasks
TDD → small reviewable change
DONE WHEN
P0 acceptance + tests
3 · 用證據完成
Validate → Release
Review actual diff
Verify acceptance + affected risk
Prepare rollback / observe
Hand off to existing release / E3
DONE WHEN
Evidence Gate + release readiness
TAKEAWAY · Golden Flow 決定下一步；Golden Default skill 決定怎麼做；risk 只改變 rigor，不改變路徑。

## Slide 8
AI Engineering：Design / Implement 各 1.5 週，總時間 8 → 6 週
8
DESIGN QUALITY
0.5 → 1.5 wk
design time ×3
FR / NFR / failure modes
AS-IS · 8 WEEKS
4 × 2-week sprints
single-repo research
unclear FR/NFR · thin tests
IMPLEMENTATION TIME
5.5 → 1.5 wk
implementation time ↓73%
less patch-driven delivery
AI · 6 WEEKS · -25%
≈ 3 × 2-week sprints
system-wide research
explicit design · TDD evidence
PATCHES / REWORK
↓ Fewer loops
validation 1.0 → 2.0 wk
TDD · staging · readiness
Illustrative target allocation：stages may overlap；需以既有 10+ pilots actual baseline 持續校準。

## Slide 9
START WITH A FEATURE
明天從一張 P1 Feature 開始：回答六個問題
9
P1 FEATURE · 60-SECOND START
1
工作在哪裡？ existing activity / system of record
2
Work Level？ P3 / P2 / P1 / P0
3
Archetype？ Greenfield / Modernization / Standard
4
Current Stage？ 第一個還不能可靠回答的問題
5
Control Profile？ rigor / risk / AI authority
WHAT CHANGES TOMORROW
Engineer
Follow Golden defaults；不再 open-ended vibe coding
Tech Lead / Architect
Approve design、equivalent skills 與 gate decisions
Manager
Integrate existing workflow；remove blockers；review outcomes
TEAM ADAPTER
Map local activity → Golden Stage / Gate / artifact
Department：minimum contract + defaults · Team：approved equivalents
從 Golden defaults 開始，用 evidence 完成；不要讓 code generation 取代 engineering。
6
Next Move？ Golden default → evidence → Gate